## User stories
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Owner | Prabin Baral
As a user, I want:
|  | No | User stories
|  | 1 | to create the snake game
|  | 2 | the game board looks like …
|  | 3 | move the snake left and right up and down with the arrow button
|  | 4 | to login to snake game from my user name
|  | 5 | see the snake moving correct direction
|  | 6 | to see when snake collides itself and die
|  | 7 | to see when snake touch the wall and die
|  | 8 | to see when the snake eat the apple and the size of snake increase
|  | 9 | score board increase by one when the snake eats the apple
|  | 10 | to get a sound when it hits to the wall , when it eats the apple and when It collide with itself.
|  | 11 | when it meets 6 and 7 conditions show the message Game over and score board
|  | 12 | the speed of snake will increase when it eats one apple.
|  | 13 | to see the highest score

## Snake-game
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Developer | Prabin Baral
No | Level-1 tasks | Level-2 tasks | Level-3 tasks | Priority | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Note
1 | Create a repository for the project on GitHub |  |  | 1 | 100% | 100%
2 | Create and update product backlog |  |  | 1 | 100% | 100%
3 | Build the snake game as in the product backlog |  |  | 2
3.1 | Redesign Snake | Build the GUI |  |  |  | 100%
3.1.1 | Redesign Gameboard |  | GUI for gameboard |  |  | 100%
3.1.2 | Redesign Pray |  | GUI for login form |  |  | 100%
3.2 |  | Build the game logic
3.2.1 |  |  | Snake logic
4 | Test and deploy the game |  |  | 3 | 0%
5 | Document the game |  |  | 4 | 0%